PROMPTRAIL Phase-Wise Implementation Timeline 18-Month Engineering Roadmap • v1.3 Enterprise Shadow AI Detection & Prevention

# Executive Overview

PromptRail is delivered across four sequential engineering phases spanning 18 months. Each phase has a defined scope, team ownership, and hard exit criteria that must be satisfied before the next phase begins. The timeline is structured to ensure working software ships incrementally — the agent is passive-monitoring capable by end of Phase 2, actively blocking by Phase 3, and fully enterprise-ready with legal compliance by Phase 4.

| Phase | Duration | Focus | Key Output |
| --- | --- | --- | --- |
| 1 | Months 1–5 | Core Interception & Protocol Hardening | Working TLS hook on all 3 OSes + QUIC blocking |
| 2 | Months 6–10 | ML Integration & Flow Classification | On-device AI detection + DLP + local LLM coverage |
| 3 | Months 11–14 | Policy Enforcement & Hardware Attestation | Active blocking + TPM attestation + browser mgmt |
| 4 | Months 15–18 | SaaS Console, Compliance & Beta Rollout | Full enterprise console + legal compliance + GA |

| Phase 1 — Core Interception, Dynamic Discovery & Protocol Hardening | Months 1–5 |
| --- | --- |

Objective

Establish reliable, low-overhead TLS plaintext capture across Linux, Windows, and macOS. Simultaneously harden the interception layer against known bypass vectors: stripped BoringSSL binaries, VPN tunnelling, QUIC/HTTP3, and WSL2/Docker network namespace isolation.

Month-by-Month Breakdown

| M1 | Project scaffolding: Rust/Aya eBPF workspace, Windows DDK environment (Visual Studio + WDK), Swift Network Extension project. CI/CD pipelines (GitHub Actions) and signing certificates obtained. Linux eBPF uprobe prototype for OpenSSL SSL_write/SSL_read on a test VM. |
| --- | --- |
| M2 | Linux: Full eBPF uprobe engine with /proc/<pid>/maps watcher and ELF dependency detection. Process metadata extraction (PID, TGID, UID, cmdline). BPF ring buffer to userspace daemon. |
| M3 | Linux: Dynamic Offset Discovery Engine — byte-pattern matching for stripped BoringSSL in Electron/Go CLI tools. CI regression test harness against BoringSSL upstream releases. WSL2 companion agent scaffolding established. |
| M4 | Windows: WFP kernel-mode callout driver. FWPM_LAYER_ALE_AUTH_CONNECT_REDIRECT_V4 → loopback proxy (127.0.0.1:9091). WFP weight management to override VPN TAP/TUN drivers. UDP/443 block to force QUIC → HTTP/2 fallback. ELAM driver prototype. |
| M5 | macOS: NETransparentProxyProvider Swift agent. Apple Notarization submitted and cleared. Cross-platform integration test: all three OSes capturing plaintext from curl, Python requests, VS Code Copilot extension, and Ollama on loopback. Phase gate review. |

Deliverables & Exit Gate

| Workstream | Key Deliverables | Exit Criteria / Gate |
| --- | --- | --- |
| Linux eBPF Engine | uprobe + uretprobe on OpenSSL, GnuTLS, BoringSSL (dynamic offset) | SSL_write hook fires on python3, curl, VS Code with 0 missed events in 1hr soak test |
| Windows WFP Driver | Callout driver + loopback redirect + VPN weight override + QUIC block | Driver WHQL-signed; no EDR alert from CrowdStrike/SentinelOne in test environment |
| macOS Network Extension | NETransparentProxyProvider capturing all NWConnection flows | Apple Notarization approved; auditing token correctly identifies process per connection |
| WSL2 Companion Agent | Lightweight Linux eBPF agent inside WSL2 + named pipe IPC | Traffic from WSL2 Python script appears in host agent telemetry |
| QUIC Blocking | UDP/443 XDP/WFP drop rules; Chrome falls back to HTTP/2 | Wireshark confirms zero QUIC flows to AI endpoints; HTTP/2 used instead |

| Phase 2 — Lightweight ML Integration & Flow Classification | Months 6–10 |
| --- | --- |

Objective

Wire the captured plaintext into a multi-layer ML classification pipeline. The agent must distinguish AI traffic from normal web traffic before decryption (Layer 1) and identify DLP violations, prompt semantics, and obfuscated payloads after decryption (Layer 2). Local LLM traffic on loopback must also be classified.

Month-by-Month Breakdown

| M6 | Dataset curation: ~500K labelled LLM API requests (OpenAI, Anthropic, Gemini, Vertex AI, AWS Bedrock, Ollama) + 1M normal web flows. JA4+ fingerprinting library integrated; ClientHello parser extracting cipher suites, TLS extensions, and ALPN. |
| --- | --- |
| M7 | Layer 1 neural network training: flow-level metadata model (packet size distribution, inter-arrival timing, byte-ratio asymmetry). gRPC streaming heuristics added: Content-Type: application/grpc detection + long-lived HTTP/2 stream lifetime features. |
| M8 | ONNX Runtime integrated into all three OS agents. Layer 1 model quantized and deployed: <2MB binary footprint, <3ms inference per flow on endpoint hardware. False positive rate validated at <0.1% on normal enterprise traffic. |
| M9 | BERT-Lite NLP model fine-tuned for DLP: PII, PCI, PHI, source code, infra configs. Quantized to ~10MB ONNX; inference within 30MB RAM. protobuf schema parser added for gRPC payload deconstruction. Schema-matching ruleset for OpenAI/Anthropic/Bedrock JSON contracts. |
| M10 | Shannon entropy analysis module. Heuristics for Base64, hex, URL-encoded payloads. Loopback interface monitoring finalized (Linux lo XDP, Windows WFP loopback flag) — local AI ports registry (11434, 1234, 8080) live. Filesystem event watcher for Ollama/LM Studio binary installation. Phase gate review. |

Deliverables & Exit Gate

| Workstream | Key Deliverables | Exit Criteria / Gate |
| --- | --- | --- |
| JA4+ Layer 1 | TLS fingerprint + flow metadata classifier | 95%+ accuracy on held-out AI vs. normal traffic dataset; FPR <0.1% |
| BERT-Lite DLP Engine | ~10MB ONNX NLP model for PII/code/IP detection | Correctly flags 98%+ of labelled PII/source code prompts in bench test |
| Entropy Analysis | Shannon entropy + Base64/hex/ROT13 heuristics | Detects >90% of obfuscated payloads in adversarial test set |
| gRPC Classification | protobuf parser + Content-Type grpc detection | Vertex AI and AWS Bedrock gRPC flows classified correctly in integration test |
| Local LLM Coverage | Loopback monitor + known port registry + fs watcher | Ollama on localhost:11434 generates DLP event visible in SOC dashboard |

| Phase 3 — Policy Enforcement, Browser Management & Hardware Attestation | Months 11–14 |
| --- | --- |

Objective

Transition the agent from passive observation to active enforcement. Implement the hierarchical policy engine, browser-managed proxy integration, TPM 2.0 remote attestation to replace software heartbeats, and the FIDO2-backed break-glass uninstall workflow.

Month-by-Month Breakdown

| M11 | Local rules engine: policy evaluation in deterministic order (Endpoint > Group > Global). Active blocking: TCP connection termination returning HTTP 403 to originating process. Policy local vault (AES-256-GCM SQLite, TPM-sealed key) with offline enforcement guarantee. |
| --- | --- |
| M12 | Browser management: Chrome Enterprise Policy (ProxySettings, SSLDecryptionEnabled) and Edge Management Service deployment pipeline. MDM-enforced browser allowlist via Intune/Jamf. WFP/Network Extension fallback for Firefox and non-MDM browsers. Process executable allowlist for portable browser detection. |
| M13 | Anti-tamper hardening: Windows PPL + ELAM driver finalized; filesystem filter driver for agent binary protection. macOS ES framework SIGTERM intercept. Linux SELinux/AppArmor profiles over BPF filesystem. TPM 2.0 PCR remote attestation: binary hash extended into PCRs at boot; cloud console verifies AIK-signed TPM Quote. |
| M14 | FIDO2 break-glass workflow: CISO YubiKey-bound offline emergency uninstall token. WORM audit log for all break-glass events. SOC alert trigger on connectivity restore. VPN TAP/TUN adapter installation detection and alerting. Full red-team exercise: 5 engineers attempt to bypass agent; all findings remediated. Phase gate review. |

Deliverables & Exit Gate

| Workstream | Key Deliverables | Exit Criteria / Gate |
| --- | --- | --- |
| Rules Engine | Hierarchical policy eval + active TCP block + offline vault | Policy change pushed from console takes effect on endpoint within 30 seconds |
| Browser Enforcement | Chrome/Edge Enterprise Proxy + MDM allowlist + fallback WFP | ChatGPT in Chrome blocked; Firefox blocked via WFP fallback; Brave detected as unapproved |
| TPM Attestation | PCR-extended boot hash + AIK-signed Quote verified by cloud console | Memory-patched agent binary causes TPM Quote mismatch; SOC containment fires within 60s |
| Break-Glass | YubiKey FIDO2 offline uninstall + WORM audit log | Break-glass generates immutable audit event; online token path still requires cloud auth |
| Red Team Gate | 5-engineer adversarial exercise against hardened agent | Zero successful undetected bypasses; all findings from exercise closed before Phase 4 |

| Phase 4 — SaaS Console, Compliance Workflows & Beta Rollout | Months 15–18 |
| --- | --- |

Objective

Deliver the enterprise-ready cloud control plane, implement all legal and privacy compliance requirements (GDPR, DPDPA, Works Council), and conduct a structured beta rollout with design partners.

Month-by-Month Breakdown

| M15 | SaaS console backend (Go + gRPC): agent registration, heartbeat ingestion, telemetry pipeline into ClickHouse. Policy CRUD API with cryptographic signing. SAML 2.0 + OIDC SSO integration (Okta, Microsoft Entra ID). Role-based access control (CISO, SOC Engineer, Read-only Auditor). |
| --- | --- |
| M16 | Frontend dashboards (React + TypeScript + Tailwind): CISO Shadow AI Discovery Matrix heat map, Data Exfiltration Prevented metrics, and adoption velocity trends. SOC Process-Level Attribution Network Graphs, Live Flow Logs with JA4 fingerprint display, and active policy rule annotations. |
| M17 | Legal & privacy compliance sprint: Audit Mode implementation (metadata-only, RAM-purge of plaintext). Zero-day retention enforcement. Data Residency locks (no cross-border plaintext transit). Four-eyes SOC approval workflow for plaintext viewing with cryptographic logging. Employee system tray UI (monitoring disclosure). Works Council approval template documentation. EULA with purpose-limitation clause. |
| M18 | SIEM/SOAR integrations: Splunk, CrowdStrike Falcon, Datadog webhooks, REST API. Beta rollout to 3–5 design partner enterprises. SLA monitoring, incident response runbooks, and on-call rotation established. GA readiness review. |

Deliverables & Exit Gate

| Workstream | Key Deliverables | Exit Criteria / Gate |
| --- | --- | --- |
| SaaS Backend | Go/gRPC console + PostgreSQL + ClickHouse + SSO | 1000 simulated agents connected; policy push latency <5s p99 |
| CISO Dashboard | Shadow AI matrix, exfiltration metrics, trend analytics | CISO can identify top-5 Shadow AI tools and data volume blocked in <2 clicks |
| SOC Dashboard | Process graphs, live logs, policy annotations, SIEM push | SOC engineer identifies process tree for a flagged event within 30 seconds |
| Compliance Mode | Audit Mode + data residency + four-eyes workflow + tray UI | Legal review sign-off from EU and India counsel; Works Council template approved |
| Beta Rollout | 3–5 enterprise design partners, incident runbooks, SLAs | Beta partners go live with zero P0 incidents in first 30 days; GA decision made |

# Master Timeline — 18-Month Gantt

| Phase | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | M13 | M14 | M15 | M16 | M17 | M18 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Phase 1 | ▪ | ▪ | ▪ | ▪ | ▪ |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Phase 2 |  |  |  |  |  | ▪ | ▪ | ▪ | ▪ | ▪ |  |  |  |  |  |  |  |  |
| Phase 3 |  |  |  |  |  |  |  |  |  |  | ▪ | ▪ | ▪ | ▪ |  |  |  |  |
| Phase 4 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | ▪ | ▪ | ▪ | ▪ |

| ■ | Phase 1: Interception | ■ | Phase 2: ML / Detection | ■ | Phase 3: Enforcement | ■ | Phase 4: Console & GA |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |